## TEAM
USER | LAST NAME | FIRST NAME
Dani | Morales Sosa | Daniel Jesús
Luis | Martín Pérez | Luis
Natasa | Đurić | Nataša
Gokan | Gligorov | Gligor

## WBS
TASK | SUBTASK | SUBTASK ESTIMATE | SUBTASK DURATION | STAGE | TASK ESTIMATE | TASK DURATION | DEVIATION
R0 |  |  |  | 0 | 0.083333 | 0.11458 | 37.5
| Idea | 0.041667 | 0.041667 | 0 |  |  | 8.5265e-14
| Description | 0.041667 | 0.072917 | 0 |  |  | 75
R1 |  |  |  | 1 | 0.16667 | 0.15417 | -7.5
| Market survey | 0.083333 | 0.081944 | 1 |  |  | -1.6667
| SWOT analysis | 0.083333 | 0.072222 | 1 |  |  | -13.3333
R2 |  |  |  | 2 | 0.3125 | 0.43542 | 39.3333
| Use cases | 0.125 | 0.14861 | 2 |  |  | 18.8889
| User stories | 0.0625 | 0.16319 | 2 |  |  | 161.1111
| Technical user stories | 0.083333 | 0.10972 | 2 |  |  | 31.6667
| Jira | 0.041667 | 0.028472 | 2 |  |  | -31.6667
R3 |  |  |  | 3 | 0.33333 | 0.4375 | 31.25
| Planning poker | 0.27083 | 0.25625 | 3 |  |  | -5.3846
| Planning with ProjectLibre | 0.0625 | 0.0625 | 3 |  |  | 0
R4 |  |  |  | 4 | 0.16667 | 0.068056 | -59.1667
| Cost estimation | 0.083333 | 0.068056 | 4 |  |  | -18.3333
| Ressource allocation | 0.083333 | 0.10417 | 4 |  |  | 25
R5 |  |  |  | 5 | 0 | 0
| Brainwriting for risk identification |  | 0 | 5
| Risk exposure |  | 0 | 5
R6 |  |  |  | 6 | 0 | 0
| Contingency plan |  | 0 | 6
R7 |  |  |  | 7 | 0 | 0
| Golden rules |  | 0 | 7
| SUS |  | 0 | 7
R8 |  |  |  | 8 | 0 | 0
| Accessibility tests |  | 0 | 8
| Static code analysis |  | 0 | 8
| Acceptance tests |  | 0 | 8
R9 |  |  |  | 9 | 0 | 0
| Model |  | 0 | 9
R10 |  |  |  | 10 | 0 | 0
| Speech preparation |  | 0 | 10
| Video recording |  | 0 | 10
PROTOTYPE |  |  |  | 11 | 0 | 0.32014
Formulas:
TASK ESTIMATE = IF([TASK]="","",SUMIF(E:E,[STAGE],C:C))
TASK DURATION = IF([TASK]="","",SUMIF(TRACKING!D:D,[TASK],TRACKING!G:G))
SUBTASK DURATION = IF([SUBTASK]="","",SUMIF(TRACKING!E:E,[SUBTASK],TRACKING!G:G))

## TRACKING
DATE | STARTING TIME | FINAL TIME | TASK | SUBTASK | AUTHOR | DURATION | NOTES
2026-05-02 | 16:15 | 16:30 | R0 | Idea | Dani | 0:15
2026-05-02 | 16:15 | 16:30 | R0 | Idea | Gokan | 0:15
2026-05-02 | 16:30 | 16:50 | R0 | Description | Gokan | 0:20
2026-05-02 | 16:00 | 16:15 | R0 | Idea | Natasa | 0:15
2026-05-02 | 16:15 | 16:50 | R0 | Description | Natasa | 0:35
2026-05-02 | 16:30 | 16:45 | R0 | Description | Dani | 0:15
2026-05-02 | 16:00 | 16:15 | R0 | Idea | Luis | 0:15
2026-05-02 | 16:15 | 16:50 | R0 | Description | Luis | 0:35
2026-12-02 | 16:20 | 16:40 | R1 | Market survey | Dani | 0:20
2026-12-02 | 16:41 | 17:08 | R1 | SWOT analysis | Dani | 0:27
2026-12-02 | 16:12 | 16:43 | R1 | Market survey | Luis | 0:31
2026-12-02 | 16:45 | 17:11 | R1 | SWOT analysis | Luis | 0:26
2026-12-02 | 16:10 | 16:42 | R1 | Market survey | Natasa | 0:32
2026-12-02 | 16:42 | 17:08 | R1 | SWOT analysis | Natasa | 0:26
2026-12-02 | 16:10 | 16:45 | R1 | Market survey | Gokan | 0:35
2026-12-02 | 16:45 | 17:10 | R1 | SWOT analysis | Gokan | 0:25
19/2/2026 | 16:45 | 17:37 | R2 | Use cases | Luis | 0:52
19/2/2026 | 16:30 | 17:37 | R2 | Use cases | Dani | 1:07
19/2/2026 | 17:39 | 17:48 | R2 | User stories | Luis | 0:09
19/2/2026 | 16:45 | 17:30 | R2 | Use cases | Gokan | 0:45
19/2/2026 | 16:40 | 17:30 | R2 | Use cases | Natasa | 0:50
19/2/2026 | 17:30 | 17:40 | R2 | Jira | Natasa | 0:10
19/2/2026 | 17:30 | 17:40 | R2 | Jira | Gokan | 0:10
26/2/2026 | 16:15 | 16:55 | R2 | User stories | Luis | 0:40
26/2/2026 | 16:05 | 16:40 | R2 | User stories | Dani | 0:35
26/2/2026 | 16:40 | 17:40 | R2 | Technical user stories | Dani | 1:00
26/2/2026 | 16:55 | 17:08 | R2 | Technical user stories | Luis | 0:13
26/2/2026 | 17:09 | 18:00 | R2 | User stories | Luis | 0:51
26/2/2026 | 16:05 | 16:55 | R2 | User stories | Gokan | 0:50
26/2/2026 | 17:00 | 17:45 | R2 | Technical user stories | Gokan | 0:45
26/2/2026 | 16:10 | 17:00 | R2 | User stories | Natasa | 0:50
26/2/2026 | 17:00 | 17:40 | R2 | Technical user stories | Natasa | 0:40
2026-05-03 | 16:31 | 17:00 | R3 | Planning poker | Luis | 0:29
2026-05-03 | 16:15 | 17:40 | R3 | Planning poker | Dani | 1:25
2026-05-03 | 17:00 | 18:00 | R3 | Planning poker | Luis | 1:00
2026-05-03 | 16:15 | 18:00 | R3 | Planning poker | Gokan | 1:45
2026-05-03 | 16:15 | 17:45 | R3 | Planning poker | Natasa | 1:30
2026-08-03 | 12:00 | 12:21 | R3 | Jira | Luis | 0:21
2026-07-03 | 16:00 | 17:30 | R3 | Planning with ProjectLibre | Dani | 1:30
2026-08-03 | 17:00 | 18:30 | R3 | Ressource allocation | Gokan | 1:30
2026-08-03 | 18:30 | 19:30 | R3 | Ressource allocation | Natasa | 1:00
2026-12-03 | 16:20 | 17:05 | R4 | Cost estimation | Dani | 0:45
2026-12-03 | 16:15 | 17:08 | R4 | Cost estimation | Luis | 0:53
2026-12-03 | 17:22 | 18:01 | PROTOTYPE | US1.1 - Query setup | Luis | 0:39
2026-12-03 | 17:08 | 17:22 | PROTOTYPE | US1.1 - Database design | Luis | 0:14
2026-12-03 | 16:04 | 18:00 | PROTOTYPE | System set up (backend and frontend) | Natasa | 1:56
2026-12-03 | 22:00 | 22:32 | PROTOTYPE | US1.1 - Query setup | Luis | 0:32
13/3/2026 | 13:30 | 13:43 | PROTOTYPE | Docker setup | Luis | 0:13
13/3/2026 | 15:11 | 17:38 | PROTOTYPE | Docker setup | Luis | 2:27
2026-12-03 | 16:10 | 17:50 | PROTOTYPE | US2.1 - Design karaoke mode UI | Gokan | 1:40

## HOURS_TASK_SUBTASK
Row Labels | Suma de DURATION
(blank) | 0:00
(blank) | 0:00
R0 | 2:45
Idea | 1:00
Description | 1:45
R1 | 3:42
Market survey | 1:58
SWOT analysis | 1:44
R2 | 10:27
Use cases | 3:34
User stories | 3:55
Jira | 0:20
Technical user stories | 2:38
R3 | 10:30
Jira | 0:21
Planning poker | 6:09
Planning with ProjectLibre | 1:30
Ressource allocation | 2:30
R4 | 1:38
Cost estimation | 1:38
PROTOTYPE | 7:41
US1.1 - Query setup | 1:11
US1.1 - Database design | 0:14
System set up (backend and frontend) | 1:56
Docker setup | 2:40
US2.1 - Design karaoke mode UI | 1:40
Grand Total | 36:43

## HOURS_PERSON_TASK
Suma de DURATION | Tarea
Row Labels | (blank) | R0 | R1 | R2 | R3 | R4 | PROTOTYPE | Grand Total
Dani |  | 0:30 | 0:47 | 2:42 | 2:55 | 0:45 |  | 7:39
Gokan |  | 0:35 | 1:00 | 2:30 | 3:15 |  | 1:40 | 9:00
Luis |  | 0:50 | 0:57 | 2:45 | 1:50 | 0:53 | 4:05 | 11:20
Natasa |  | 0:50 | 0:58 | 2:30 | 2:30 |  | 1:56 | 8:44
(blank) | 0:00 | [6 empty] | 0:00
Grand Total | 0:00 | 2:45 | 3:42 | 10:27 | 10:30 | 1:38 | 7:41 | 36:43

## HOURS_PERSON_DAY
Suma de DURATION | Miembro
Row Labels | Dani | Gokan | Luis | Natasa | (blank) | Grand Total
2026-12-02 | 0:47 | 1:00 | 0:57 | 0:58 |  | 3:42
19/2/2026 | 1:07 | 0:55 | 1:01 | 1:00 |  | 4:03
26/2/2026 | 1:35 | 1:35 | 1:44 | 1:30 |  | 6:24
(blank) |  |  |  |  | 0:00 | 0:00
2026-05-03 | 1:25 | 1:45 | 1:29 | 1:30 |  | 6:09
2026-08-03 |  | 1:30 | 0:21 | 1:00 |  | 2:51
2026-07-03 | 1:30 |  |  |  |  | 1:30
2026-05-02 | 0:30 | 0:35 | 0:50 | 0:50 |  | 2:45
2026-12-03 | 0:45 | 1:40 | 2:18 | 1:56 |  | 6:39
13/3/2026 |  |  | 2:40 |  |  | 2:40
Grand Total | 7:39 | 9:00 | 11:20 | 8:44 | 0:00 | 36:43